## reply
BHARAT SANCHAR NIGAM LIMITED
(A GOVT OF INDIA ENTERPRISE)
Electrical wing
From |  |  | To
O/o The Subdivisional Engineer € |  |  | O/o The Executive Engineer€
BSNL ABM Emtce |  |  | 7th floor, BSNL ED-II,
16A, Greams Road, |  |  | Ethiraj salai
Chennai |  |  | Chennai
Sub :-Operation & Comprehensive AMC of various EM Services for BSNL Admin. Bldg. at Greams Road, Chennai. (SH: Comprehensive maintenance of Electrical Installation, Substation, Fire Protection system, Associated equipments of DG set/ UPS and Operation of EM Services) (For a Period of 12 Months)
Ref # :- | Recovery item / CEE/ TNEZ/ Ch/2022/ 75 dt 04.04.2022
EE€/ ED II 's Lr # 23(9)/ EEE /ED II/BSNL/ Ch /2022/89
With reference to the letter cited above, the following pointwise reply is furnished as desired
sl # | questonaire from O/o CE€, BSNL TNEZ , Chennai | reply
1 | Recovery for which period of operation and maintenance | AMC is for the period 01.04.2019 to 04.11.2020. the recovery statement pertains to 5 th running account & final bill proposed for AMC of EMS for EI works as per agreement terms and conditions , forwarded for the period 01.08.2020 to 04.11.2020 . |  | AMC is for the period 01.04.2019 to 04.11.2020. The recovery statement pertains to the 5 th running account & final bill for the period 01.08.2020 to 04.11.2020.
2 | The agreement pertains to 19-20, why the recovery item statement was sent belatedly after two years. | Recovery item statement for 3rd , 4 th running account bill forwarded from this office on 18.03.2021 and the recovery approval for the same is received by this office 15.01.2022. recovery proposed for the 5 th and final bill as per agreement terms and conditions , had been forwarded to division office via email on 18.08.2021 also to the firm , and the same had been forwarded from this office on 31.08.2021 and handed over to division office for further approval . |  | The agreement came to a close on 04.11.2020 and the recovery statement for the final bill was sent on 18.08.2021. Hence the observation that there was a delay of 2 years is incorrect. The following points are submitted for further clarity. The approval for the recoveries proposed in the previous bills (3rd & 4th RA bills) was awaited. The statements for the same were sent to Division on 18.03.2021. However, as the approval was getting delayed, the recovery statement for the final bill was also forwarded on 18.08.2021 through email and 31.08.2021 through hard copy. It is also intimated that the approval for the previous recovery statements was received only on 15.01.2022
3 | How SDE€ can propose a recovery and condone it, which amounts to transgressing the authority. | The undersigned has due respect for higher end authorities and discharging her duties for the sake and interest of BSNL only and also undersigned neither deviated her work nor disobeyed the higher authorities at any instance . In 3 rd and 4 th RA bill, for the above, item is condoned by O/O SE(E) , but the same problem persists up to the period of date of completeion of AMC (04.11.2020).However, Based on the oral instruction of O/O EE(E), the above item is mentioned in the statement and in remarks column as per the previous orders it has shown as condoned item only . Undersigned never transgress the higher authority at any time . |  | SDE(E) has not condoned any recovery or transgressed her authority. In 3rd and 4th RA bills, the recoveries proposed for certain items were condoned by the SE(E). As these deficiencies / lapses were not rectified in the ensuing period also by the Contractor, Recovery for these items were proposed in the final statement also. However, for indicative purpose, a mention was made in the remarks column that the recoveries for these items have been condoned in the previous bills. SDE(E) has not certifed anywhere that the deficiencies / lapses are condoned.
4 | Some of the items have been installed /rectified belatedly . What action was taken to replace those item and when they were replaced | Even after repeated reminders to the firm , the firm fails to attend /rectify the faults within AMC period. Hence, Reasonable time allowed for the firm to set right the fault , hence the faults /non working of the same are reduced.(necessary correspondence mails are enclosed for your kind perusal) |  | SDE(E) cannot act independently as the Engineer-in-charge is EE(E). All the correspondence to the Contractor by this office is marked to EE(E) also for information. Unless there is specific direction from EE€, the SDE€ cannot be blamed for inaction. To support this claim, some of the mail correspondences of this office with the Vendor and EE(E) are enclosed.
5 | It seems that the site incharge resorted to only recovery for delays and no action seems to have been taken to set the instruments , which are vital for opeartion of the installation , in to working condition. Please provide explanantion for the same. | This office had initiated to execute the work for some of the items . but two instance , the firm fails to participate, and also spot quotation received by this office had been forwarded to division office for approval. |  | The observation appears to be prejudiced in nature because the data for the allegation has not been called for. However, it is clarified that action was taken by this office to attend to the deficiencies at the risk and cost of the Contractor, on two occasions but there was no response from bidders. Also, Spot quotations were obtained and forwarded to Division office for approval. EE (E) is well aware of this fact.
6 | Recovery for 40 nos of faulty Exit sign board has been proposed in the referred statement . In this regard the following details to be submitted
a | since when the EXIT signs were faulty | from 03.07.2020, 22.07.2020( email correspondence letter enclosed for your kind information)
b | Whether the same are rectified , and if rectified the date of rectification | No.
c | If rectified,how they are rectified, whether through risk and cost or by the AMC agency and cost of rectification if done at risk and cost method | Nil.however, in recovery statement , as per agreement terms and conditions , for rectification of the fault , the risk and cost amount is proposed for the same . |  | Not rectified by the Contractor. As payment cannot be made to the Contractor for unperformed tasks, recovery was proposed, to protect the interests of BSNL.
d | the present status of faulty EXIT signs | At present there are 49 EXIT signs which are still under faulty condition .(40+9 in electrical store)
The draft DE will be forwarded to division office for the same to rectify the EXIT sign faults .
Note
Final bill format with recovery forwarded to division office via email on 18.08.2021, w/o response from the firm , the bill is forwarded to division office on 31.08.2021